## Sheet1
=DISPIMG("ID_8C5AB065770A4157AA04F732ED68CC32",1) |  | From | https://szdiscus.com/
|  | Email | sourcing03@discus-hc.com
|  | Phone number: | +86 13048842095
|  | WhatsApp: | +86 13048842095
Logistics and Delivery Services Details
No. | Module Category | Sub-item | Detailed Content / Implementation Standards | Deliverable | Responsible Party | Remarks
1 | Project Basic Information | Project Name | Fill in the full project name (e.g., XX Brand Sunscreen Tube Packaging Upgrade Design Project) | Project Initiation Confirmation Form | Both Parties | Lock the core boundary of the project
2 |  | Brand & Product Positioning | Brand tonality, core product selling points, target audience, competitor benchmarking analysis report | Market Research & Analysis Report | Designer Team (Party B) | Provide data support for design strategy
3 |  | Core Packaging Requirements | Packaging type (tube/bottle/box/pouch), material & process, size specification, target market (Domestic/Europe & America/Southeast Asia), compliance requirements (China Cosmetics Regulation/EU CPNP/FDA) | Requirement Specification Document | Client Contact (Party A) | Lock the compliance bottom line and implementation requirements of the design
4 | Creative Concept Design | Design Style Direction | Output 3 sets of differentiated creative style solutions, matching brand tonality and product positioning, including color system, visual elements and layout logic | Creative Concept Design Draft (PDF) | Lead Designer (Party B) | Each set includes cover, style description and core visual display
5 |  | Concept Solution Review | Party A reviews the 3 sets of solutions, selects 1 main solution and puts forward modification opinions | Solution Review Confirmation Letter | Both Parties | Lock the final design direction and enter the deepening stage
6 |  | Solution Optimization & Adjustment | Optimize the selected solution based on Party A's review opinions, and complete the initial visual draft | Optimized Initial Visual Draft (AI/PDF) | Designer Team (Party B) | Includes full-view design of front, back and sides
7 | Structure & Process Implementation | Packaging Structure Design | Match materials and production processes, complete packaging die-cut drawing and structure exploded view, confirm size, opening and closing method and load-bearing adaptability | Packaging Structure Die-cut Drawing (AI/CAD) | Structural Designer (Party B) | Adapt to factory production equipment and mass production requirements
8 |  | Process & Material Adaptation | Clarify printing process (foil stamping/UV/embossing), material selection and surface treatment process, and output process specification document | Process & Material Specification | Designer + Process Consultant (Party B) | Cooperate with factory production feasibility to avoid implementation risks
9 |  | Compliance Information Typography | Complete the standardized typography of compliance information such as ingredient list, instructions for use, filing number and warning words in accordance with the regulations of the target market | Final Draft of Compliance Information (AI) | Designer + Compliance Specialist (Party B) | Ensure compliance with domestic and foreign cosmetic supervision requirements
10 | Visual Deepening & Specification Output | Final Design Draft Output | Complete the full expansion drawing, 3D effect drawing and scene rendering of the packaging, and confirm that all visual elements, texts and sizes are error-free | Final Design Draft File (AI/PDF/PSD) | Designer Team (Party B) | Can be directly used for proofing and production
11 |  | Brand Visual Specification Extension | Output the brand visual usage specifications supporting the packaging, including color values, font specifications and logo usage rules | Packaging Visual Specification Manual (PDF) | Design Director (Party B) | Ensure the unity of subsequent brand vision
12 | Proofing & Implementation Adaptation | Proofing File Output | Provide mass production-level production files to the factory, including die-cut drawing, printing color separation file and process annotation file | Full Set of Production & Proofing Files | Designer Team (Party B) | Comply with factory printing/production standards
13 |  | Proofing Follow-up & Adjustment | Follow up the factory proofing process, check the consistency between the sample and the design draft, and make fine adjustments for color difference and process deviation | Proofing Check Confirmation Form | Designer (Party B) + Client Contact (Party A) | Confirm the final mass production sample
14 | Final Delivery & After-sales Service | Full Delivery Package Sorting | Sort out the full-process delivery documents of the project, file them by category, and provide cloud disk download link | Full Project Delivery Package | Project Contact (Party B) | Includes all design source files, specification files and production files
15 |  | After-sales Support | Provide design Q&A and file fine-tuning support during the mass production stage, for a period of 3 months after delivery | After-sales Support Service | Designer Team (Party B) | Ensure the smooth implementation of mass production
Other requirements can be discussed separately.